## Compensation_Events
CE ID | Description | Category | Status | Cost Impact (£) | Delay Impact (Days) | Critical Path? | Date Notified
CE-01 | Discovery of Uncharted Gas Main | Site Conditions | Implemented | 125000 | 12 | Yes | 2026-01-15
CE-02 | Additional Piling at River Irwell | Design Change | Implemented | 280000 | 8 | Yes | 2026-02-10
CE-03 | Signal Box Design Revision | Client Instruction | Under Assessment | 45000 | 4 | No | 2026-03-05
CE-04 | Ground Obstructions at Depot | Site Conditions | Notified | 85000 | 15 | Yes | 2026-03-22
CE-05 | Subcontractor Insolvency (Track) | Contractor Risk | Rejected | 0 | 22 | Yes | 2026-04-12
CE-06 | Exceptional Rainfall - Feb 2026 | Weather Delay | Under Assessment | 110000 | 6 | Yes | 2026-03-01

## Weather_Baseline
Month | Actual Rainfall (mm) | 1-in-10 Yr Rainfall Baseline (mm) | Actual Days Rain > 5mm | 1-in-10 Yr Days Rain > 5mm Baseline | Actual Days Temp < 0°C | 1-in-10 Yr Days Temp < 0°C Baseline
January | 112 | 135 | 8 | 11 | 4 | 7
February | 145 | 120 | 14 | 10 | 2 | 5
March | 92 | 105 | 7 | 8 | 0 | 2
April | 64 | 85 | 4 | 6 | 0 | 0